## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
WP8 Project management
Milan Gocić
University of Niš
Kick-off meeting/ 16th December 2016
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: Documents and guidelines
Erasmus+ programme guide
NatRisk application
Grant agreement
Partnership agreement
Guidelines for the use of the grant
Recommendations from the grant award criteria/project evaluation report and later recommendations from all other reports on project implementation
Erasmus+ Dissemination platform
Decisions, strategies, guidelines, etc. generated within the Consortium
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 3: Grant agreement
Special conditions
Annex I – Description of the action
Annex II - General conditions
Annex III - Estimated budget of the action
Annex IV - List and mandates of the beneficiaries
Annex V - Model Technical report
Annex VI - Model Financial statement
Annex VII - Guidance notes - Report of Factual Findings on the Final Financial Report - Type II
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 4: Partnership agreement
A Partnership Agreement is a compulsory commitment that must be agreed and signed by each beneficiary organisation and should be consistent with the provisions as laid out in the Grant Agreement (and its annexes).
A copy of the Partnership Agreement will have to be provided to the Agency within 6 months of the signature of the Grant Agreement.
The Partnership Agreement must be signed by the legal representative of each of the beneficiary organisations.
The Partnership Agreement can either be multilateral (single agreement signed by the coordinator and all the other beneficiary organisations) or bilateral (a different agreement signed between the coordinator and each beneficiary organisation).
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 5: Partnership agreement
beneficiaries' rights and obligations
beneficiaries' role and responsibilities
management and governance modalities
financial management and related rules
reporting mechanisms
conflict management mechanisms in case of problems or tasks/activities not properly implemented
communication strategy (project website, dissemination and exploitation plan)
sustainability strategy
other relevant topic for the efficient implementation of the project
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 6: General obligations and role of the coordinator
Monitor that the action is implemented in accordance with the Grant Agreement
Be the intermediary for all communications between the beneficiaries and the Agency
Immediately provide the Agency with the information related to any change of any of the beneficiaries or to any event likely to affect or delay the implementation of the action
Bear responsibility for supplying documents and information to the Agency which may be required
Where information is required from the other beneficiaries, the coordinator shall bear responsibility for obtaining and verifying this information before passing it on to the Agency
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 7: General obligations and role of the coordinator
Make the appropriate arrangements for providing any financial guarantees under the Agreements
Establish the requests for payment in accordance with the Agreement
Ensure that the appropriate payments are made to the other beneficiaries without unjustified delay
Bear responsibility for providing all the necessary documents in the event of checks and audits initiated before the payment of the balance, and in the event of evaluation
Transfer to all beneficiaries, without delay, document(s) relating to the action or the grant.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 8: General obligations and role of the beneficiaries
Be jointly and severally responsible for carrying out the action in accordance with the Agreement
Be responsible for complying with any legal obligations incumbent on them jointly or individually
Make proper internal arrangements for the proper implementation of the action
Inform immediately the coordinator of any change likely to affect the delay in implementation, or any other change in name, address, or any legal, financial, technical, organisational or ownership situation
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 9: General obligations and role of the beneficiaries
Submit in due time to the coordinator: the data needed to drew up records, financial statements or other documents; all necessary documents in the events of audits, checks or evaluation; and any other information to be provided to the Agency
All partners including the Coordinator are responsible for promoting the fact that financing is provided from the European Union funds in the framework of the Erasmus+ programme.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 10: Financial Management
Pre-financings (First and Second pre financing):
first pre-financing payment of 50% of the maximum amount specified in Article I.3 of the Grant Agreement will be paid to the coordinator.
second pre-financing payment of 40% of the maximum amount specified in Article I.3 shall be paid to the coordinator, subject to the following conditions:
  having used at least 70% of the previous pre-financing instalment paid;
  the receipt of the "Statement of the costs incurred" and "Request for payment" as specified in Annex VI of the Grant Agreement;
  the receipt of a progress report on implementation of the action as specified in Annex V of the Grant Agreement.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 11: Reporting obligations/modalities
Reporting is a contractual obligation that has to be fulfilled by all the beneficiaries.
Although it is the coordinator's responsibility to submit the reports and their mandatory supporting documents in due time, the completion of the reports and the validation of the information they contain is a responsibility that falls under each of the beneficiaries that compose the project partnership.
In case the coordinator fails definitively to submit the project reports and the related required supporting documents, the Agency shall recover any amount already paid and if applicable, apply financial penalties of between 2% and 10% of the value of the grant as stipulated under Article II.17.1 of the Grant Agreement.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 12: Progress report on the implementation of the action
The progress report on the implementation of the action will have to be submitted half way through the eligibility period i.e. on 14/04/2018 at the latest.
It consists of the following:
  Technical report on the implementation of the project (description of the progress made, statistics and indicators, tables of achieved/planned outcomes, etc.)
  Summary report for publication
  Statement of the costs incurred ('intermediate Financial Statement‘)
  Request for payment of the second pre-financing (to be submitted only when 70% of the first pre-financing has been spent)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 13: Request for the second pre-financing
The coordinator can submit together with the "Technical report on the implementation of the project" the "Request for payment" of the second pre-financing as specified in Annex VI of the Grant Agreement in case 70% of the previous pre-financing instalment has been used.
In case 70% of the previous pre-financing instalment has not been used half way through the eligibility period, the progress report on the implementation of the action (together with the Statement of the costs actually incurred) should be submitted without the Request for payment of the second pre-financing.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 14: Final report
The Final report on implementation of the action will have to be submitted at the latest two months after the end of the contractual period i.e. on 14/12/2019 at the latest.
It consists of the following:
  Final Technical report on the implementation of the project (description of the results and achievements, statistics and indicators, table of achieved outcomes, etc.)
  Summary report for publication
  Final Financial Statement and Request for payment - including the financial tables for each budget heading and the required supporting documents
  Report of Factual Findings on the Final Financial Report – Type II (Audit Certificate on the action's financial statements and underlying accounts)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 15: Reports
Development of master curricula for natural disasters risk management in Western Balkan countries
Coordinator Reports delivered to EACEA (two reports) | Progress Report – 14.04.2018
 | Final report – 14.12.2019
Partner’s Financial Report delivered to coordinator (six reports) | 1st report – 14.04.2017
 | 2nd report – 14.10.2017
 | 3rd report – 14.03.2018
 | 4th report - 14.10.2018
 | 5th report - 14.04.2019
 | 6th report - 14.10.2019
Partner’s Technical report on the implementation of the project delivered to coordinator (six reports) | 1st report – 14.04.2017
 | 2nd report – 14.10.2017
 | 3rd report – 14.03.2018
 | 4th report - 14.10.2018
 | 5th report - 14.04.2019
 | 6th report - 14.10.2019

## Slide 16: Project management tasks
Establishment of Steering Committee and Project Management Committee.
Organisation of kick-off and management meetings.
Development of guidelines on the project management and reporting.
Organisation of day-to-day coordination.
Submission of interim and final reports.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 17: WP8 activities
Development of master curricula for natural disasters risk management in Western Balkan countries
8.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14.11.2016
8.2 Regular Steering Committee and Project Management meetings | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions (BOKU, UNIME, UNID, TUC, MUHEC, UNSA) | 14.10.2019
8.3 Development of guidelines on the project management and reporting | 
Guidelines on the project management and reporting created - UNI in consultation with contact persons from all institutions | 14.03.2017
8.4 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14.10.2019