## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Planned and realised activities
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"
Emina Hadžić
University of Sarajevo
NEO BiH Monitoring visit to the project/ 15th September 2017

## Slide 2
Development of master curricula for natural disasters risk management in Western Balkan countries
UNSA project team:
Prof. Emina Hadžić – team leader (manager) - FCE
Prof. Naida Ademović – teacher - FCE
Prof. Dženana Bijedić – teacher - AF
Prof. Slobodanka Ključanin – teacher - FCE
Prof. Admir Mulahusić – teacher - FCE
Ass. Adis Skejić – teacher - FCE
Ass. Hata Milišić – teacher - FCE
Ass. Ammar Šarić – technical and administrative staff - FCE
Mirza Mehaković – administrative staff - UNSA

## Slide 3: Workplan for project year 1
Development of master curricula for natural disasters risk management in Western Balkan countries
Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | Identification of natural disasters to be managed in WB | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.2 | Introduction with established practices in EU countries for NDRM | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.3 | Workshop on master curricula best practices in EU countries | 11 |  |  |  |  | 3= | 4= | 4X= |  |  |  |  | 
2.1 | Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 11 |  |  |  |  |  | 2X | 2X | 2X | 2X | 3X |  | 
2.2 | Development of courses content and syllabi | 26 |  |  |  |  |  | 3X | 3X | 4X | 4X | 4X | 4X | 4X
2.3 | Training of teaching staff for innovative teaching methods | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
2.4 | Providing of students’ internships positions | 1 |  |  |  |  |  |  |  |  | X | X | X | X
2.5 | Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 11 |  | 2X | 2X | X | X | X | 2X | 2X |  |  |  | 
3.1 | Surveillance of citizens’ and public sector awareness regarding natural disasters | 16 |  | 2X | 3X | 3X | 4X | 4X |  |  |  |  |  | 
3.2 | Study visits and analysis of courses best practices in EU countries | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
3.3 | Development of trainings’ content corresponding educational materials and selection of teaching staff | 9 |  |  |  |  |  |  |  |  |  | 3X= | 3X | 3X
4.1 | Defining of admission requirements and enrolment of students | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.2 | Implementation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.3 | Implementation of students’ internships | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.4 | Implementation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.5 | Self-evaluation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.6 | Self-evaluation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.1 | Regular Quality Assurance Committee meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
5.2 | Development of the quality control plan | 6 | 2X= | 2X= | 2X= |  |  |  |  |  |  |  |  | 
5.3 | Conduct external review of the project | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.4 | External financial control | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.5 | Inter-project coaching | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.1 | Creation of the dissemination plan for the project | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
6.2 | Development and maintenance of project website and creation of promotional materials and campaigns | 10 |  | 2X | 2X= | X= | X= | X= | X | X | X | X | X | X
6.3 | Promotional activity for student enrolment | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.4 | Promotional activity for trainings | 2 |  |  |  |  |  |  |  |  |  |  | X | X
7.1 | Creation of sustainability plan | 6 |  | 2X= | 2X= | 2X= |  |  |  |  |  |  |  | 
7.2 | Accreditation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
7.3 | Realization of student and staff mobilities between WB and EU partners | 0 |  |  |  |  |  |  |  |  |  |  |  | 
8.1 | Kick-off meeting | 2 | 3X= |  |  |  |  |  |  |  |  |  |  | 
8.2 | Regular Steering Committee and Project Management meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
8.3 | Development of guidelines on the project management and reporting | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
8.4 | Day-to-day coordination of project activities | 15 | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X=
8.5 | Submission of interim and final reports | 0 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: WP1 – to do list Analysis of natural disasters needed to be managed in Western Balkan region
Development of master curricula for natural disasters risk management in Western Balkan countries
1.1 Identification of natural disasters to be managed in WB | 
Identification of natural disasters needed to be managed in WB and assessment of all risk management aspects. Identification of natural disasters needed to be managed in BIH. Preparation of the report for BOKU meeting in Vienna. | March 2017 COMPLETED
1.3 Workshop on master curricula best practices in EU countries | 
Report on master curricula best practices in EU partners and Catalogue of competencies - BOKU in consultation with contact persons from all institutions (Workshop in Vienna, 4-8 April 2017) | 14 May 2017 Workshop COMPLETED

## Slide 5: WP2 – to do list Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.1 Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 
Defined aims, specific competencies and learning outcomes of master curriculum per HEI in WB; Catalogue of courses – All WBC institutions | September 2017 In progress
2.2 Development of courses content and syllabi | 
Defined courses content and syllabi – All WBC institutions | December 2017 In progress
2.3 Training of teaching staff for innovative teaching methods | 
Teaching staff trained – EU partners in a colaboration with WBC institutions Obuda University (24-25 May 2017) Middlesex University (29-30 June 2017) Technical University of Crete (10-11 July 2017) | December 2017 In progress

## Slide 6: WP2 – to do list Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.5 Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 
The equipment specification was made (April 2017) Preparation of tendering procedure | October 2017 In progress

## Slide 7: WP3 – to do list Development of trainings for citizens and public sector
Development of master curricula for natural disasters risk management in Western Balkan countries
3.1 Surveillance of citizens’ and public sector awareness regarding natural disasters | 
Survey of citizens’ and public sector awareness | April 2017 COMPLETED
3.3 Development of trainings’ content corresponding educational materials and selection of teaching staff | 
Trainings’ materials prepared, teachers selected - UNID in consultation with contact persons from all WBC institutions | 14 February 2018 Forthcoming

## Slide 8: WP5 – to do list Quality assurance and monitoring
Development of master curricula for natural disasters risk management in Western Balkan countries
5.1 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – (first: BOKU April 2017, second: UNIME September 2017) | 14 October 2019 In progress

## Slide 9: WP6 – to do list Dissemination
Development of master curricula for natural disasters risk management in Western Balkan countries
6.1 Creation of the dissemination plan for the project | 
Dissemination plan created – UNI in consultation with contact persons from all institutions | March 2017 COMPLETED
6.2 Development and maintenance of project website and creation of promotional materials and campaigns | 
Promotion material created – All WBC institutions | 14 October 2019 In progress
6.4 Promotional activity for trainings | 
Trainings promoted - All WBC institutions | 14 October 2019 Forthcoming

## Slide 10: WP7 – to do list Exploitation
Development of master curricula for natural disasters risk management in Western Balkan countries
7.1 Creation of sustainability plan | 
Sustainability plan created – UNI in consultation with contact persons from all institutions | March 2017 COMPLETED

## Slide 11: WP8 – to do list Project management
Development of master curricula for natural disasters risk management in Western Balkan countries
8.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14 November 2016 COMPLETED
8.2 Regular Steering Committee and Project Management meetings | 
First SC and PM meeting – Vienna (April 2017) Second Steering Committee meeting – Messina (September 2017) | 14 October 2019 In progress
8.3 Development of guidelines on the project management and reporting | 
Guidelines on the project management and reporting created - UNI in consultation with contact persons from all institutions | 14 March 2017 COMPLETED
8.4 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14 October 2019 In progress

## Slide 12: Next steps to be taken
To purchase equipment and software for the laboratory; to install the equipment and software (October 2017)
Development of courses content and syllabi (December 2017)
Signed final version of SMS contracts (October 2017)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 13: Administrative and financial issues
Development of master curricula for natural disasters risk management in Western Balkan countries
Staff Costs | 26,019.00
Travel Costs | 8,125.00
Costs of Stay | 19,310.00
Equipment Costs | 33,800.00
Subcontracting Costs | 3,000.00
Special Mobility Strand | 42,337.00
TOTAL | 132,591.00
Total budget: 1.245.746,00 EUR
UNSA: 132.591,00 EUR
First grant: 14.906,50 EUR (20 March 2017)
Second grant: In progress
First financial report: Prepared; needs to be signed
Travel costs and costs of stay: Financed by team members (not refunded)
Staff costs: Report created; not paid yet

## Slide 14: Thank you for your attention!
Development of master curricula for natural disasters risk management in Western Balkan countries