## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Overview of the achieved results and future tasks
Milan Gocić
University of Niš
Sixth Steering Committee meeting/ 05th September 2019
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: WP1 – COMPLETED Analysis of natural disasters needed to be managed in Western Balkan region
Development of master curricula for natural disasters risk management in Western Balkan countries
1.1 Identification of natural disasters to be managed in WB | 
Report on natural disasters in WB – BOKU in consultation with contact persons from all WBC institutions | 14 March 2017 COMPLETED
1.2 Introduction with established practices in EU countries for NDRM | 
Survey of established practices in EU countries for NDRM – BOKU in consultation with EU partners institutions | 14 March 2017 COMPLETED
1.3 Workshop on master curricula best practices in EU countries | 
Report on master curricula best practices in EU partners and Catalogue of competencies - BOKU in consultation with contact persons from all institutions (Workshop in Vienna, 4-8 April 2017) | 14 May 2017 COMPLETED

## Slide 3: WP2 – COMPLETED Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.1 Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 
Defined aims, specific competencies and learning outcomes of master curriculum per HEI in WB; Catalogue of courses – All WBC institutions | 14 August 2017 COMPLETED
2.2 Development of courses content and syllabi | 
Defined courses content and syllabi – All WBC institutions | 14 December 2017 COMPLETED
2.3 Training of teaching staff for innovative teaching methods | 
Teaching staff trained – EU partners in a colaboration with WBC institutions Note: 1) May 2017 - OE (19 staff): UNI - 6, KPA - 3, UPKM - 3, VSUP - 2, TCASU - 2, UNID – 3 2) June 2017 - MUHEC (14 staff): UNI - 6, UPKM - 3, UNSA - 3, TCASU – 2 3) July 2017 - TUC (20 staff): UNI - 6, KPA - 3, UPKM - 3, UNSA - 3, VSUP - 2, UNID – 3 4) September 2017 – UNIME (19 staff): UNI - 6, UPKM - 3, UNSA - 3, VSUP - 2, TCASU - 2, UNID – 3 5) November 2017 - BOKU (12 staff): UNI - 6, KPA - 3, UNSA - 3 | 14 December 2017 COMPLETED

## Slide 4: WP2 – to do list Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.4 Providing of students’ internships positions | 
Agreements for internships signed - All WBC institutions (KPU – 2, TCASU – 1, UBL – 1, UNID – 1, UNI – 1, UNSA – 1, UPKM - 1) | 14 October 2019 COMPLETED
2.5 Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 
Laboratories equipped – All WBC institutions | 14 June 2017 COMPLETED

## Slide 5: WP3 – COMPLETED Development of trainings for citizens and public sector
Development of master curricula for natural disasters risk management in Western Balkan countries
3.1 Surveillance of citizens’ and public sector awareness regarding natural disasters | 
Survey of citizens’ and public sector awareness – UNID in consultation with contact persons from all WBC institutions | 14 April 2017 COMPLETED
3.2 Study visits and analysis of courses best practices in EU countries | 
Study visit reports – In conjuction with 2.3 | 14 December 2017 COMPLETED
3.3 Development of trainings’ content corresponding educational materials and selection of teaching staff | 
Trainings’ materials prepared, teachers selected - UNID in consultation with contact persons from all WBC institutions | 14 February 2018 COMPLETED

## Slide 6: WP4 – to do list Implementation of developed master curricula and trainings
Development of master curricula for natural disasters risk management in Western Balkan countries
4.1 Defining of admission requirements and enrolment of students | 
Students enrolled WB HEIs should define admission requirements | 14 October 2018 In progress
4.2 Implementation of master curricula | 
Master curricula implemented | 14 October 2019 In progress
4.3 Implementation of students’ internships | 
Students’ internships realized – 10 UNI to UNSA, 5 KPU to UBL, 5 UNID to UBI, 5 UPKM to UNI, 2 TCASU to KPA, 5 UNSA to UNI, 5 UBL to KPA EU examples of students’ internships organisation (report) | 14 October 2019 In progress

## Slide 7: WP4 – to do list Implementation of developed master curricula and trainings
Development of master curricula for natural disasters risk management in Western Balkan countries
4.4 Implementation of trainings for citizens and public sector | 
Participants trained – planned 420 participants/trained 474, 14 trainings organised | 14 September 2019 COMPLETED
4.5 Self-evaluation of master curricula | 
Quality report on master curricula | 14 September 2019 In progress
4.6 Self-evaluation of trainings for citizens and public sector | 
Quality report on trainings 14 reports written | 14 September 2019 COMPLETED

## Slide 8: WP5 – to do list Quality assurance and monitoring
Development of master curricula for natural disasters risk management in Western Balkan countries
5.1 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – MUHEC in consultation with representatives from UNI, BOKU, OE (sixth: UNSA 4 September 2019) | 14 October 2019 COMPLETED
5.2 Development of the quality control plan | 
Quality control plan adopted – MUHEC in consultation with contact persons from UNI, BOKU, OE | 14 January 2017 COMPLETED
5.3 External evaluation of the project | 
Report of the external quality evaluation - Mid-term external evaluation of the project – 01 September 2018, second 01 September 2019 | 14 May 2018 COMPLETED

## Slide 9: WP5 – to do list Quality assurance and monitoring
Development of master curricula for natural disasters risk management in Western Balkan countries
5.4 External financial control | 
Report of the external auditor - Mid-term external evaluation – end of September 2018 | 14 July 2019 In progress
5.5 Inter-project coaching | 
Report on the inter-project coaching – March 2018 | 14 May 2018 COMPLETED

## Slide 10: WP6 – to do list Dissemination
Development of master curricula for natural disasters risk management in Western Balkan countries
6.1 Creation of the dissemination plan for the project | 
Dissemination plan created – UNI in consultation with contact persons from all institutions | 14 March 2017 COMPLETED
6.2 Development and maintenance of project website and creation of promotional materials and campaigns | 
Promotion material created Website and platform launched | 14 October 2019 In progress
6.3 Promotional activity for student enrolment | 
Student enrolment promoted - All WBC institutions | 14 October 2018 COMPLETED
6.4 Promotional activity for trainings | 
Trainings promoted - All WBC institutions | 14 October 2019 COMPLETED

## Slide 11: WP7 – to do list Exploitation
Development of master curricula for natural disasters risk management in Western Balkan countries
7.1 Creation of sustainability plan | 
Sustainability plan created - UNI in consultation with contact persons from all institutions | 14 March 2017 COMPLETED
7.2 Accreditation of master curricula | 
Documentation to the national commissions should be sent till March 2018. | 14 October 2018 In progress
7.3 Realization of student and staff mobilities between WB and EU partners | 
26 Inter-institutional agreements signed. | 14 October 2019 In progress

## Slide 12: WP8 – to do list Project management
Development of master curricula for natural disasters risk management in Western Balkan countries
8.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14 November 2016 COMPLETED
8.2 Regular Steering Committee and Project Management meetings | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions (fifth: MUHEC 20-21 March 2019, sixth: UNSA 5 September 2019) | 14 October 2019 COMPLETED
8.3 Development of guidelines on the project management and reporting | 
Guidelines on the project management and reporting created - UNI in consultation with contact persons from all institutions | 14 March 2017 COMPLETED
8.4 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14 October 2019 In progress

## Slide 13: WP8 – to do list Project management
Development of master curricula for natural disasters risk management in Western Balkan countries
8.5 Submission of interim and final reports | 
Interim and final reports submitted – UNI in consultation with contact persons from all institutions | 14 October 2019 In progress